## Sheet1
Task Breakdown
Task Number | Task Description | Date Due (Planned) When you intend to complete the task | Date Completed (Actual) When you actually completed the task
1 | Create a user stories list | 2025-03-14 | 2025-03-14
2 | Create a design guide | 2025-03-14 | 2025-03-14
3 | Create a high-fidelity wireframes with Figma | 2025-03-14 | 2025-03-14
4 | Begin writing source code for initial website | 2025-03-15 | 2025-03-15
5 | Create a development plan for JS features and website | 2025-03-15 | 2025-03-15
6 | Begin implementing js into source code and have a initial version of the website | 2025-03-16 | 2025-03-16
7 | Finish Home Page Implementation | 2025-03-18 | 2025-03-18
8 | Finish Things to Do Page | 2025-03-21 | 2025-03-22
9 | Finish Gift Shop and About page | 2025-03-23 | 2025-03-24
10 | Begin preparing user testing materials | 2025-03-25 | 2025-03-26
11 | Reach out to potential users and conduct testing | 2025-03-25 | 2025-03-26
12 | Based on feedback, update code and other | 2025-03-26 | 2025-03-27
13 | Write design summary | 2025-03-27 | 2025-03-28